## Test plan
Solution OXE only | OT | TEST CASE # | FEATURE | TEST / CHECK DESCRIPTION | Set type to be tested | [8 empty] | Additional information | PASSED / FAILED | Comments
[5 empty] | IP | TDM | Z | SIP | OTC PC SIP | GSM nat | GSM internat. | PSTN nat. | PSTN internat.
|  | 1 | START/Configuration
|  | 1.1 | Registration in the operator’s proxy | UNI mode tests only
Y | Y | 1.1.1 | Configure OXE in order to have it registering a range of phone numbers on the public network | config menus are available | [10 empty] | passed | Timer 480
Y | Y | 1.1.2 | Configure OXE in order to have it registering a range of phone numbers on the public network / (with or without authentication) / set a correct number range. Check REGISTER messages exchanged. (check particularly "expires" values in request and answer) | Registration is OK. "Expires" timer is correctly used for refresh. - SIP UTI looks like : sip:+e164_number@My_sip_provider_domain - contact header looks like : sip:+e164_installation_number@IP_address_of_IPPBX | [9 empty] | if applicable | passed | expires sent Tmer 480 expires Timer received 120 re-registration after 96 sec
Y | Y | 1.1.3 | Configure OXE in order to have it registering a range of phone numbers on the public network / (with or without authentication) / set a bad operator number range in OXE config. Check REGISTER messages exchanged. (check particularly "retry-after" header in the answer) | Registration is NOT OK. Check OXE retries to register after "retry-after" timer if sent by operator. | [9 empty] | if applicable | passed
|  | 1.2 | Authentication
Y | Y | 1.2.1 | Configure OXE and operator in order to have SIP trunk in authenticated mode towards the operator (DIGEST authenticated on operator side) | config is possible | [10 empty] | passed
Y | Y | 1.2.2 | DIGEST authenticated on operator side / correct secret | outgoing and incoming calls are possible. Check call flows ( RFC 2617 and RFC 1321 are used for outgoing calls) (see "Some Call flows checks" part) | X (any) |  |  |  |  | X (any) |  |  |  | if applicable | passed
Y | Y | 1.2.3 | DIGEST authenticated on operator side / incorrect secret | Outgoing call is impossible. Check call flows ( RFC 2617 and RFC 1321 are used for outgoing calls) | X (any) |  |  |  |  | X (any) |  |  |  | if applicable | passed
|  | 2 | VOICE CALLS : site 1 and PSTN or GSM
|  | 2.1 | 1PCC OUTGOING CALLS
|  | 2.1.0 | Basics to GSM sets
Y | Y | # 2100 | OXE device calls to GSM set : outcall phase and com. establishment | ring / (remote or local, please tell) ringback, normal audio after answer. Check the display of the calling number. | X |  |  |  |  | X (any) |  |  |  | If OT user, have a look at OTC PC display also | passed
Y | Y | # 2101 | OXE device calls GSM set: end of com. by local party | com. and trunk properly released | X |  |  |  |  | X (any) |  |  |  | If OT user, have a look at OTC PC display also | passed
Y | Y | # 2102 | OXE device calls GSM set : end of com. by remote party | com. and trunk properly released | X |  |  |  |  | X (any) |  |  |  | If OT user, have a look at OTC PC display also | passed
Y | Y | # 2103 | OXE device calls to GSM set : outcall phase and call clearing before answer | com. and trunk properly released - Check SIP call flow. CANCEL sent by OXE /OK answered by Network./ then 487 sent by OXE / Ack from network. | X |  |  |  |  | X (any) |  |  |  | If OT user, have a look at OTC PC display also | passed | Cancel sent by OXE 487 sent by network OK sent by network ACK sent by OXE
Y | Y | # 2104 | OXE device calls to GSM set : outcall to a wrong number | Correct display and trunk properly released | X |  |  |  |  | X (any) |  |  |  | If OT user, have a look at OTC PC display also | passed | different behaviour depenending on Provider (announcement)
Y | Y | # 2105 | OXE device calls to GSM set : outcall to a busy set | Correct display and busy tone. busy tone heard. (check SIP/SDP traces) | X |  |  |  |  | X (any) |  |  |  | If OT user, have a look at OTC PC display also | passed | busy here sent by provider
|  | 2.1.1 | 1PCC Basics to PSTN sets
Y | Y | # 2110 | OXE device calls to PSTN set : outcall phase and com. establishment | ring / remote ringback, normal audio after answer | X | [6 empty] | X (any) |  | If OT user, have a look at OTC PC display also | passed | no trace but ok
|  | 2.1.3 | Anonymous outgoing calls
Y | Y | # 2130 | OXE device to public number : outcall with CLIR | identity of caller not displayed on callee side. | X | [6 empty] | X |  |  | passed
N | Y | # 2131 | OT user to public number : outcall with CLIR | identity of caller not displayed on callee side. | [7 empty] | X
|  | 2.2 | INCOMING CALLS
|  | 2.2.1 | Incoming basic calls with CLI (no overflow to attendant configured)
Y | Y | # 2210 | incoming public call to OXE device : com. Establishment. End call by any party. | display CLI info on callee sides, normal conversation / check SIP trace and from parameter. - Check display is consistent with FROM or PAI parameter. - check SDP Offer/Response exchange - Check Ring back tone on public side | X |  |  |  |  | X |  | X |  | If OT user, have a look at OTC PC display also | passed
Y | Y | # 2211 | incoming public call to Oxe node 1 set: call clearing before answer | display CLI info on caller and callee sides, normal conversation / check SIP trace. - Check SIP call flow. CANCEL sent by network /OK answered by OXE./ then 487 sent by network/ Ack from OXE. | X | [6 empty] | X |  | If OT user, have a look at OTC PC display also | passed | Canceled sent by network OK by OXE 487 Request Terminated by OXE ACK by network
N | Y | # 2215 | incoming public call to mono-device OT user : com. Establishment. End call by any party. | display CLI info on callee and caller sides, normal conversation / check SIP trace and from parameter. - Check display is consistent with FROM parameter. - check SDP Offer/Response exchange - Check Ring back tone on public side | [5 empty] | X (any) |  |  |  | If OT user, have a look at OTC PC display also
N | Y | # 2216 | incoming public call to multi-devices OT user : call clearing before answer | display CLI info on caller and callee sides, normal conversation / check SIP trace. - Check SIP call flow. CANCEL sent by network /OK answered by OXE./ then 487 sent by network/ Ack from OXE. | [5 empty] | X (any)
|  | 2.2.2 | Anonymous incoming calls from public
Y | Y | # 2220 | Incoming call from public network with secret identity to OXE device. | Check that identity is not displayed on Callee side in ringing phase, and in connected phase neither. - Check SIP traces : URI in FROM header should look like : "Anonymous" <sip:anonymous@anonymous.invalid>;tag=1928301774 - Check if P-Asserted ID is avalable in messages | X |  |  |  |  | X |  | X |  | If OT user, have a look at OTC PC display also | passed | Proxy Id on IP-Address must be TRUE otherwise call not established
N | Y | # 2221 | Incoming call from public network with secret identity to OT user. | Check that identity is not displayed on Callee side in ringing phase, and in connected phase neither. - Check SIP traces : URI in FROM header should look like : "Anonymous" <sip:anonymous@anonymous.invalid>;tag=1928301774 - Check if P-Asserted ID is avalable in messages | [5 empty] | X (any) |  |  |  | If OT user, have a look at OTC PC display also
|  | 2.3 | 1PCC routing services
|  | 2.3.2 | DDI call / subscriber's call forwarding (to internal or voicemail) :
Y | Y | # 2320 | Incoming call: immediate forward to VB (voicemail-box) | CLI and audio-msg in VB of the right callee/ no SIP 302 sent to public network. / possible to navigate in the menus with DTMF | X |  |  |  |  | X |  |  |  |  | passed
Y | Y | # 2321 | * inc. PSTN : immediate forward to other internal user | Audio OK / no SIP 302 message sent to public network. | [7 empty] | X (any) |  |  | passed | display on destination shows forwarded call
|  | 2.3.4 | DDI call / subscriber's call forwarding (to external)
Y | Y | # 2340 | incoming Public call to OXE user : immediate forward to public number | display # or name of initial callee on caller side, normal audio after answer / SDP transparency (for supported codecs by OXE) for offer/answer /no SIP 302 message sent to network. /tromboning done on OXE side / check header History Info is present with OXE user number | X (any) | [6 empty] | X |  |  | passed | Forwarding done by Re_Invite Display correct Registration ID P-Asserted must be set TRUE
Y | Y | # 2341 | incoming Public call to OXE user: fwd on no answer to public number. | display # or name of initial callee on caller side, normal audio after answer / SDP transparency (for supported codecs by OXE) for offer/answer /no SIP 302 message sent to network. /tromboning done on OXE side | X (any) | [6 empty] | X |  |  | passed
N | Y | # 2342 | incoming Public call to OT user : immediate forward to public number | display # or name of initial callee on caller side, normal audio after answer / SDP transparency (for supported codecs by OXE) for offer/answer /no SIP 302 message sent to network. /tromboning done on OXE side |  |  |  |  | X (user level) |  |  | X
N | Y | # 2343 | incoming Public call to OT user: fwd on no answer to public number. | display # or name of initial callee on caller side, normal audio after answer / SDP transparency (for supported codecs by OXE) for offer/answer /no SIP 302 message sent to network. /tromboning done on OXE side |  |  |  |  | X (user level) |  |  | X
|  | 2.3.5 | DDI call / subscriber not available
Y | Y | # 2350 | * inc. PSTN : OXE NODE 1 set Do Not Disturb | in SIP traces, 480 temporarily unavailable message is sent to network. It is handled by network in a correct manner. | X | [6 empty] | X |  |  | passed
Y | Y | # 2351 | * inc. PSTN : OXE NODE 1 non attributed number | Call is freed by OXE (404) or overflow to operator (according to OXE config) | X | [6 empty] | X |  |  | passed | 404 Not Found Provider sends announcement
Y | Y | # 2352 | incoming public call to busy OXE user | Normal busy tone is heard on caller side. SIP 486 user busy sent to network. It is handled by network in a correct manner. | X |  |  |  |  | X (any) |  |  |  |  | passed
N | Y | # 2353 | incoming public call to busy OT user | Normal busy tone is heard on caller side. SIP 486 user busy sent to network. It is handled by network in a correct manner. | [5 empty] | X (any)
|  | 2.4 | Advanced FEATURES for COMMUNICATION
|  | 2.4.1 | 1PCC Enquiry call (call hold / call retrieve)
Y | Y | # 2410 | incoming public call to OXE set : put on-hold and retrieve communication | Music on hold is heard on caller side. Check SIP traces. RE-INVITEs - OK sent between OXE and network. off-hold is OK also. | X | [6 empty] | X |  |  | passed | Re-Invite is answered with challenge by provider
N | Y | # 2411 | incoming public call to OT user : put on-hold and retrieve communication | Music on hold is heard on caller side. Check SIP traces. RE-INVITEs - OK sent between OXE and network. off-hold is OK also. | [7 empty] | X
|  | 2.4.3 | Early attended transfer (on ringing)
Y | Y | # 2430 | public call on going with OXE set : transfer to other OXE internal set | display (no evolution of display on public side), Ring back tone on public side. After answer normal audio, clean release | X |  |  |  |  | X (any) |  |  |  |  | passed
Y | N | # 2431 | public call on going with OXE set : transfer to other OT internal set | display (no evolution of display on public side), Ring back tone on public side. After answer normal audio, clean release | X |  |  |  |  | X (any) |  |  |  |  | N/A
Y | Y | # 2432 | public call on going with OXE set : transfer to ext number | tromboning is done on OXE side, no display change on initial caller. Display on second public callee is OXE user, even after answer. | X |  |  |  |  | X (any) |  |  |  |  | passed | Ringback, number displays ok
N | Y | # 2433 | public call on going with OT user: 1 step transfer to other OT internal set (use of "transfer to" button) | display (no evolution of display on public side), Ring back tone on public side. After answer normal audio, clean release | [5 empty] | X (any)
N | Y | # 2434 | public call on going with OT user: 1 step transfer to other OXE internal set (use of "transfer to" button) | display (no evolution of display on public side), Ring back tone on public side. After answer normal audio, clean release | [7 empty] | X
N | Y | # 2435 | public call on going with OT user: 1step transfer to ext number (use of "transfer to" button) | tromboning is done on OXE side, no display change on initial caller. Display on second public callee is initial caller, even after answer. | [7 empty] | X
|  | 2.4.4 | Supervised call transfer (after answer).
Y | Y | # 2440 | public call ongoing with an OXE set : transfer to other OXE set (wait for second callee answer before transfering) | display (no evolution of display on public side). After transfer normal audio, clean release. Final callee has display of external. | X | [6 empty] | X |  |  | passed
N | Y | # 2441 | public call ongoing with an OXE set : transfer to OT user (wait for second callee answer before transfering) | display (no evolution of display on public side). After transfer normal audio, clean release. Final callee has display of external. | X | [6 empty] | X |  |  | N/A
Y | Y | # 2442 | public call ongoing with an OXE set : transfer to public set (wait for second callee answer before transfering) | tromboning is done on OXE side, no display change on initial caller. Display on second public callee is OXE user. | X | [6 empty] | X |  |  | passed
N | Y | # 2443 | public call ongoing with an OT user : transfer to other OT user (wait for second callee answer before transfering) | display (no evolution of display on public side). After transfer normal audio, clean release. Final callee has display of external. |  |  |  |  | X |  |  | X
N | Y | # 2444 | public call ongoing with an OT user : transfer to other OXE user (wait for second callee answer before transfering) | display (no evolution of display on public side). After transfer normal audio, clean release. Final callee has display of external. |  |  |  |  | X |  |  | X
N | Y | # 2445 | public call ongoing with an OT user : transfer to public set (wait for second callee answer before transfering) | tromboning is done on OXE side, no display change on initial caller. Display on second public callee is OXE user. |  |  |  |  | X |  |  | X
|  | 2.4.5 | Conference (3-party)
Y | Y | # 2451 | 2 Public sets and 1 OXE set which has generated conference | displays are globally OK (the name of all participants is not displayed on public side => normal), normal audio. Check the end of conf is handled correctly | X | [6 empty] | X |  |  | passed
N | Y | # 2455 | Public and 2 OT sets (conf generated with "add" button) | displays are globally OK (the name of all participants is not displayed on public side => normal), normal audio. Check the end of conf is handled correctly | [7 empty] | X
N | Y | # 2457 | Public and 2 OT sets (conf generated by "merge" of 2 calls) | displays are globally OK (the name of all participants is not displayed on public side => normal), normal audio. Check the end of conf is handled correctly |  |  |  |  | X |  |  | X
|  | 2.4.6 | DTMF : Sent to public network
Y | Y | # 2460 | outgoing call to an external IVR from OXE user: DTMF to external server. | Check that the DTMF code are well accepted by the remote server / RFC2833 is used | X | [9 empty] | passed
|  | 3 | 3PCC specificities
|  | 3.1.2 | Piloting a public device from My IC PC
N | Y | # 3121 | OXE user : OTC PC launches a 3PCC call to public number from public set | display, normal audio/ check display on My IC PC application on caller side. | X | [6 empty] | X
|  | 3.1.3 | Call Admission Control related tests.
Y | Y | # 3130 | Incoming call from public network when CAC is saturated. | Check call is rejected properly / 503 is corrrecly sent and accepted by network | X (any) |  |  |  | X | X |  |  |  |  | passed
|  | 5 | FAX TRANSMISSION
|  | 5.1.1 | Fax transmission with fax machine attached on OXE
Y | Y | # 5110 | Multiple pages (3) Fax transmit to PSTN from OXE fax machine | Check fax transmission is done. | [9 empty] | Fax mode tested : T38 / G711 / Both with fallback | passed | T38 with Fallback 5 pages Transmission in G711
Y | Y | # 5111 | Multiple pages (3) Fax receive from public net to OXE FAX machine | Chek fax transmission is done. | [9 empty] | Fax mode tested : T38 / G711 / Both with fallback | passed | G711 only only working option
|  | 5.2.1 | Fax transmission from Fax server
N | Y | # 5210 | A multiple pages fax is sent over PSTN from fax server | Check that fax is correctly transmitted. Note the audio codec used during fax transmission. | [9 empty] | Fax mode tested : T38 / G711 / Both with fallback
|  | 5.2.2 | Fax reception by Fax server
N | Y | # 5220 | A multiple page fax is received from PSTN by fax server | Check that fax is correctly received (note which audio codec is used during call setup.) | [9 empty] | Fax mode tested : T38 / G711 / Both with fallback
|  | 7 | Inter-working with applications
|  | 7.1.1 | My Messaging
N | Y | # 7110 | Step 1 : Call the voice mail number from a public phone set through SIP trunk. Step 2 :Press some touch keys to navigate the menu. | Step 1 : Check that a menu is heard Step 2 : Check that it is possible to browse the menu. | X | [6 empty] | X
N | Y | # 7111 | Step 1 : From a GUI client select a voice message that has previously been left by a public phone. Ask for call back sender Step 2 : Answer the call | Step 1 : Check that public phone is called back Step 2 : Check that call is OK Step 3 : Check displays are consistent. | X | [6 empty] | X
N | Y | # 7112 | Step 1 : From a GUI client select a voice message that has previously been left by a public phone. Ask for call back sender from a public set also. (other device or mobile) Step 2 : answer your own public set Step 3 : Answer the call on callee side. | Step 1 : Check that public phone is called back Step2 : Ring back tone is heard on caller public set. Step 3 : Check that call is OK Step 4 : Check displays are consistent. | X (any) |  |  |  | X (any) |  |  | X

## Read me
Scope
This paper is a test descriptive to be used to validate the SIP trunking interface of the Alcatel-Lucent OpenTouch and OmniPCX Enterprise systems. The test suite here will allow to check the behavior of SIP system features (Registration, Outbound proxy, Supervision, Security) and SIP user services (Basic call, CLIP/CLIR, Call Forwarding, Call Hold, Transfer, DTMF …) in OXE / SIP provider interworking - i.e check the compliance of the SIP implementation with OT/OXE and the SIP provider network. This test campaign does not test all possible configuration combinations. If during the test, tester changes configuration for any reason, then he must specify it in the "3.Template_Config_OXE_SIP_Providers.xls" document, and he must be aware of the possible impacts for the already executed tests and re-execute the impacted ones. At the end of the test, the final configuration has to be recorded in document "3.Template_Config_OXE_SIP_Providers.xls"
<_ Alcatel-Lucent OmniPCX Enterprise release x.x and/or OpenTouch release y.y _>
<_ Country _>
<_SIP provider name_>
Glossary and how to
CCS | Call Control Server
CLI | Calling Line Identification.
CLIP | Calling Line Identification Presentation
CLIR | Calling Line Identification Restriction
COLP | Connected Line Identification Presentation
COLR | Connected Line Identification Restriction
CS | Call server
DDI | Direct Dialling In
GD | Media Gateway board
GK | Gatekeeper
IP | Internet Protocol
MCID | Malicious Call Identification
OXE | OmniPCX Enterprise
PE | Public Exchange
PSTN | Public Switched Telephone Network
SDP | Session Initiated Protocol
SIP | Session Initiation Protocol
VoIP | Voice over IP
OT ICM user | Open Touch user, not standard (OXE) user
1PCC | First Party Call control
3PCC | Third Party Call Control
Reference: ENT_MLE_015803_test_plan
Ed13 November 2016